## Time Log
Date	Start	End		Description
08/18/15	02:00 PM	03:15 PM	75	Met with manager Dr. Gorka about project expectations and requirements
08/20/15	02:00 PM	02:30 PM	30	Met with Dr. Gorka for clarification on a few aspects of the project. Initial brief description of project seems to meet requirements
08/20/15	04:50 PM	05:30 PM	40	Downloaded documents from PLATO, created project journal, and began and completed proposal introduction.
08/20/15	07:45 PM	09:15 AM	90	Began and completed proposal breadth requirements.
08/23/15	07:40 PM	08:00 PM	20	Began project depth requirements. Researched cross-functional team definition. Created resources document to log information sources for project.
08/24/15	09:30 PM	10:00 PM	30	Continued project depth requirements.
08/25/15	10:10 AM	10:45 AM	25	Reviewed proposal draft feedback from Dr. Gorka. Made appropriate changes to proposal draft breadth requirements.
08/25/15	01:20 PM	01:55 PM	35	Revising project depth and breadth requirements.
08/25/15	02:00 PM	02:15 PM	15	Met with Dr. Gorka for update on project development. Clarification on meaning of network breadth requirement.
08/30/15	06:34 PM	06:35 PM	1	Reviewed Dr. Gorka's journal 2 feedback.
08/31/15	07:42 PM	09:00 PM	78	Reviewed Dr. Gorka's proposal draft 2 feedback. Reviewed bandwidth. Researched project needs including WAMP version, hardware, and page sizes and updated project proposal breadth requirements. Brainstormed for project name. Created proposal presentation using project proposal as a guide.
09/01/15	09:00 AM	09:55 AM	55	Completed proposal presentation
09/03/15	02:00 PM	02:05 PM	5	Presented initial project proposal to stakeholders.
09/03/15	09:00 PM	09:50 PM	50	Expanded project proposal summary summarizing specifications and information added on 8/31
09/09/15	09:20 AM	09:35 AM	15	Downloaded and reviewed proposal draft 3 feedback. Created note in project summary that searching will be referred to as querying. Changed sentence wording in Programming Breadth Requirement and Research Area slightly.
09/10/15	04:00 PM	04:10 PM	10	Met with Dr. Gorka for weekly meeting due to class cancellation on Tuesday. Received pre-preliminary approval to begin working on project until proposal is reviewed again.
09/14/15	07:20 PM	08:00 PM	40	Created estimated timeline. Thought of what needs to be done and guessed how long it would take.
09/14/15	11:30 PM	11:31 PM	1	Reviewed Dr. Gorka's feedback. Received preliminary approval.
09/15/15	02:00 PM	02:10 PM	10	Met with Dr. Gorka. Initial review of Estimated Time-line was good. Minor changes need to be made.
09/17/15	08:10 AM	08:25 PM	15	Made small changes to Estimated Time-line
09/19/15	10:25 AM	10:31 AM	6	installed wamp
09/19/15	10:31 AM	10:49 AM	18	Identified actors (Advertisers, Users, Leader, Moderator, Administrator, Email Server, Time)
09/19/15	10:49 AM	11:27 AM	38	Worked on Context Diagram, Use Cases
09/22/15	01:40 PM	01:55 PM	15	Database table design
09/22/15	02:10 PM	02:20 PM	10	Met with Dr. Gorka. Initial review of Estimated Time-line was good. Minor changes need to be made.
09/23/15	09:00 AM	09:40 AM	40	Researched secure development practices.
09/23/15	12:15 PM	12:17 PM	2	Met with Dr. Gorka about research area and how much security I should try to add.
09/25/15	06:00 PM	06:30 PM	30	Started to design database. Brainstormed table and field requirements
09/26/15	07:00 PM	07:40 PM	40	Continued database design and use cases. New use cases and field requirements keep being brought up so they will most likely be continually developed as more pages and functions are added.
09/28/15	09:00 PM	10:00 PM	60	Brainstormed required pages and sketched layout possibilities.
09/28/15	10:00 PM	11:50 PM	120	Started coding initial page layouts focusing mostly on the 'header' and 'footer' that will be used on all of the pages.
09/28/15	11:50 PM	12:00 PM	10	Created a front page graphic for guests, similar to the Facebook landing page.
09/29/15	02:00 PM	02:05 PM	5	Met with Dr. Gorka. Showed her page development.
09/30/15	12:20 PM	12:40 PM	20	Looked into OWASP recommendations for password storage. Found that GET and Post requests are not secure and SSL seems to require significant effort so save for later implementation if possible.
10/03/15	02:20 AM	03:00 AM	40	Looked into prepared statements. Could not get sample code to work even after using code exactly like an example and checking spelling. Finally figured out that the phpmyadmin account I was using for the query only had select permissions.
10/03/15	12:00 PM	12:15 PM	15	Tried using phpmyadmin account with write permissions to execute query. It worked.
10/03/15	12:50 PM	01:20 AM	30	Continued and finished work on password storage: hashing and salting.
10/03/15	02:40 PM	03:30 PM	50	Retrieve password from database through prepared statements. Getting SQL syntax just right was time consuming: column and table names do not need to have quotations
10/03/15	04:50 PM	05:30 PM	40	Implemented code to change password. Prepared statement was causing issues again. After a lot of trial and failure I had to look up how to get the error message. Apparently accounts need select privileges to perform update statements.
10/03/15	05:35 PM	05:50 PM	15	Implemented 'invalid username or password' notification code for login.
10/03/15	07:10 PM	07:30 AM	20	Implemented barebones profile page
10/03/15	09:40 PM	12:00 AM	140	Worked on session and add session pages.
10/04/15	02:20 AM	02:35 AM	15	Sessions can now be created by users
10/04/15	10:20 PM	10:55 PM	35	Moved add session to session page. Added comment section to session and user pages. Cannot create comments yet
10/05/15	12:10 AM	12:50 AM	40	Users can post comments to session and user pages
10/05/15	03:45 PM	07:00 PM	195	Implemented 'deleting' comments. Installed MySQL workbench to reverse engineer. Added relationships to database tables. Translated userID's that are displayed in comments to usernames by changing sql statement to have a join with the user table.
10/05/15	11:35 PM	01:20 AM	95	Created presentation for interim report.
10/06/15	01:20 AM	02:00 AM	40	Created interim report document.
10/06/15	12:30 PM	12:40 PM	10	Presented interim report.
10/07/15	12:00 PM	12:25 PM	25	Join/Leave session button now only visible to logged in users. Looked into jquery/ajax style tag system similar to youtube – will implement in the future after required functionality
10/07/15	12:25 PM	12:40 PM	15	Create session form now only visible by logged in users.
10/07/15	12:40 PM	12:43 PM	3	Added more fields to session search form
10/08/15	11:00 PM	12:20 AM	80	Added account recovery/password reset
10/11/15	08:00 PM	08:30 PM	30	Added changing password and account bio
10/12/15	12:45 PM	01:50 AM	65	Added changing session settings. SQL was throwing errors and took a while to debug. The problem turned out to that 'limit' is a reserved word and was using as such instead of a column name. Column name was changed to 'cap' to resolve issue.
10/13/15	01:20 PM	01:45 PM	25	Started the 'feed' feature that shows recent events. It currently shows everyone's comments and where they were made
10/13/15	05:00 PM	05:30 PM	30	Started validating input for registration form
10/15/15	01:00 PM	02:30 PM	60	Finished form validation for registering and creating sessions. Added charset method statements to database connections to hopefully prevent against 2nd order sql injections.
10/15/15	06:00 PM	07:00 PM	60	Changed datetime selection method because the script that was being used was clunky. There is now a more aesthetic interface for date selection and dropdown menus for hour, minute, and period. Added updated column to session table to record when they are changed for use in feeds
10/15/15	10:00 PM	10:35 PM	35	Added security to editing sessions: you must be leader or admin/mod.
10/15/15	10:35 PM	11:20 PM	45	Cleaning code to implement methods calls for data validation instead of various implementations on various pages.
10/20/15	02:08 PM	02:35 PM	27	Met with Dr. Gorka. Showed her various parts of the system and what a user can do. Showed which requirements have been fulfilled.
10/21/15	09:30 AM	09:40 AM	10	Fixed unset editSessionError and unset userID error messages in edit session page
10/21/15	09:50 AM	09:58 AM	8	Added messages when password and bio is updated successfully in user settings
10/21/15	12:00 PM	01:00 PM	60	Implemented friends: friend request, cancel request, accept request, and remove friend
10/21/15	05:00 PM	05:10 PM	10	Friend list now displays on profiles with clickable links to those friends
10/22/15	08:00 PM	08:40 PM	40	Changed activity feed so that only activity involving friends is displayed
10/23/15	10:30 AM	11:20 AM	50	Edit session form now auto fills and editing works again
10/25/15	10:00 PM	10:30 PM	30	Implemented auto-logout for admins and mods. This was not implemented for normal users since sites like Facebook with much more personal information on it does not feel the need.
10/26/15	11:20 PM	11:50 PM	30	Changed comment to actually delete instead of 'hide'. Implemented logging of all sql statements that are executed.
10/26/15	11:50 PM	12:05 AM	15	Added ability to delete sessions.
10/29/15	05:40 PM	06:30 PM	50	Researched and used online resources to generate Acceptable Use Policy, Terms of Use Policy, and Privacy Policy
10/29/15	07:20 PM	07:50 PM	30	Converted and formatted policies correctly and added to site.
10/29/15	07:50 PM	07:56 PM	6	Added checkbox for users to agree to policies when registering.
10/30/15	12:00 AM	12:25 PM	25	Emails can now be sent from my server. I previously thought that there was a much more in depth process required but only two settings in the php.ini file (smtp server and originating email)
11/02/15	12:50 PM	01:00 PM	10	Added changing visibility to edit session
11/02/15	05:00 PM	06:30 AM	90	CSS, Contact form now sends emails
11/03/15	05:00 PM	06:00 PM	60	Help page, About page
11/03/15	07:30 PM	08:40 PM	50	FAQ, Max 100 characters show for description in sessions list
11/04/15	05:40 PM	06:50 PM	70	Defined software and hardware requirements
11/05/15	01:35 PM	01:40 PM	5	Met with Dr. Gorka for final approval on remaining project requirements
		Total	2983	minutes
			49.7166666667	hours

## Resource Log
Resources
http://www.oxforddictionaries.com/us/definition/american_english/cross-functional	08/24/15	cross functional definition
https://www.youtube.com/watch?v=RiY2ja-OTnA	08/31/15	bandwidth refresher
http://www.wampserver.com/en/	08/31/15	wamp specs
pingdom.com	08/31/15	page size
http://www.whoishostingthis.com/blog/2010/04/14/bandwidth-needed/	08/31/15
https://www.owasp.org/index.php/OWASP:About	09/23/15	secure programming practices
http://php.net/manual/en/language.operators.string.php	09/27/15	joining strings in php
https://css-tricks.com/php-include-from-root/	09/27/15	php get root
https://c2.staticflickr.com/6/5048/5280585822_ed883a633a_b.jpg	09/28/15	graphic
https://pixabay.com/static/uploads/photo/2013/07/12/17/51/linked-152575_640.png	09/28/15	graphic
http://stackoverflow.com/questions/5678567/how-to-pass-variables-between-php-scripts	09/28/15
http://stackoverflow.com/questions/8935704/div-position-fixed-on-the-top-of-web-page	09/28/15
http://stackoverflow.com/questions/727958/what-is-the-best-way-to-left-align-and-right-align-two-div-tags	09/28/15
http://www.w3schools.com/css/css_display_visibility.asp	09/28/15
http://stackoverflow.com/questions/12209438/logout-button-php	09/28/15
http://www.w3schools.com/php/php_sessions.asp	09/28/15
http://stackoverflow.com/questions/15220704/how-to-detect-if-post-is-set	09/28/15
https://www.virendrachandak.com/techtalk/php-isset-vs-empty-vs-is_null/	09/28/15
http://www.w3schools.com/html/html_form_elements.asp	09/28/15
http://programmers.stackexchange.com/questions/30076/login-using-email-or-username	09/28/15
http://www.w3schools.com/tags/att_input_placeholder.asp	09/28/15
http://stackoverflow.com/questions/5065281/how-to-enable-ssl-in-wamp-server	09/30/15	ssl
http://www.javascriptkit.com/script/script2/tengcalendar.shtml	10/03/15	datetime picker
http://stackoverflow.com/questions/2871866/mysqli-php-check-if-sql-insert-query-was-fully-successful-using-mysqli	10/03/15
http://stackoverflow.com/questions/6379752/php-pdo-what-do-dbh-and-sth-stand-for	10/03/15
http://stackoverflow.com/questions/23071427/singleton-class-for-database-mysqli-phpversion-5-2-17	10/03/15
http://stackoverflow.com/questions/4488035/call-to-a-member-function-bind-param-on-a-non-object	10/03/15
http://stackoverflow.com/questions/1219809/mysqli-prepare-statement-returning-false-but-why	10/03/15
http://stackoverflow.com/questions/17284294/php-mysqli-prepared-insert-statement-fails	10/03/15
https://www.owasp.org/index.php/Password_Storage_Cheat_Sheet	10/03/15
http://stackoverflow.com/questions/2235434/how-to-generate-a-random-long-salt-for-use-in-hashing	10/03/15
http://stackoverflow.com/questions/8335828/how-to-delete-post-variable-upon-pressing-refresh-button-on-browser-with-php	10/03/15
http://stackoverflow.com/questions/11927968/document-root-php	10/03/15
http://board.phpbuilder.com/showthread.php?10381656-for-loop-with-fetch_assoc	10/03/15
http://stackoverflow.com/questions/24466455/codeigniter-removing-index-php-from-url-in-wamp	10/08/15
http://stackoverflow.com/questions/4391530/how-to-use-htaccess-in-wamp-server	10/08/15
http://stackoverflow.com/questions/12202387/htaccess-not-working-apache	10/08/15
http://stackoverflow.com/questions/8371634/how-to-hide-php-extension-in-htaccess	10/08/15
http://stackoverflow.com/questions/6396294/php-get-array-value-with-a-numeric-index	10/08/15
http://stackoverflow.com/questions/1008668/how-secure-is-a-http-post	10/08/15
http://stackoverflow.com/questions/14267010/how-to-create-self-signed-ssl-certificate-for-test-purposes	10/08/15
http://stackoverflow.com/questions/5065281/how-to-enable-ssl-in-wamp-server	10/08/15
http://stackoverflow.com/questions/6216125/unset-form-submit-button	10/08/15
http://stackoverflow.com/questions/1355728/values-of-disabled-inputs-will-not-be-submited	10/08/15
https://upload.wikimedia.org/wikipedia/commons/thumb/0/08/Simple_icon_time.svg/1280px-Simple_icon_time.svg.png	10/08/15
https://upload.wikimedia.org/wikipedia/commons/thumb/2/28/White_X_in_red_background.svg/2000px-White_X_in_red_background.svg.png	10/15/15
http://www.ascii.cl/htmlcodes.htm	10/15/15
https://jqueryui.com/datepicker/	10/21/15
http://www.pontikis.net/blog/dynamically-bind_param-array-mysqli	10/21/15
https://www.rocketlawyer.com/	10/29/15
https://www.sophos.com/en-us/medialibrary/PDFs/other/sophosexampleITacceptableusepolicy.ashx	10/29/15
http://www.lipsum.com/feed/html	10/29/15
http://stackoverflow.com/questions/14853756/track-all-mysql-queries-in-wamp	10/29/15
https://frontier.com/HelpCenter/Residential/Categories/internet/email/troubleshooting-email/get-started/mail-server-settings	10/30/15
http://stackoverflow.com/questions/7820225/how-to-send-email-from-local-wamp-server-using-php	10/30/15
http://roshanbh.com.np/2007/12/sending-e-mail-from-localhost-in-php-in-windows-environment.html	10/30/15
http://www.colorzilla.com/gradient-editor/	11/02/15
http://stackoverflow.com/questions/520237/how-do-i-expire-a-php-session-after-30-minutes	11/02/15
http://stackoverflow.com/questions/24733328/sql-in-statement-for-multiple-columns	11/02/15
http://stackoverflow.com/questions/134099/are-pdo-prepared-statements-sufficient-to-prevent-sql-injection/12202218#12202218	11/02/15
http://stackoverflow.com/questions/3219178/php-how-to-get-local-ip-of-system	11/03/15
https://confluence.atlassian.com/doc/server-hardware-requirements-guide-30736403.html	11/03/15
https://www.quora.com/How-much-Internet-bandwidth-do-enterprises-purchase-per-1000-users	11/03/15

## Estimated Timeline
To Do List
Thing	Time (minutes)	Deadline
Download and Install WAMP	10	09/19/15
Identify actors	30	09/19/15
Use case analysis	60	09/19/15
Research Secure Programming Methods (secure database development, secure programming)	240	09/23/15
Design database	30	09/25/15
Implement database	120	09/25/15
Analyze Interface Requirements (What webpages need to be created, what data they need to display)	180	09/27/15
Question possible clients for what they like to see in web interfaces compared to commonly used examples today such as social media	180	09/30/15
Design Interface (draw pictures)	60	10/01/31
Implement Interface (write html/css)	600	10/04/15
Develop matching algorithm	120	10/07/15
Add Record PHP Methods	60	10/08/15
Modify Record PHP Methods	120	10/08/15
Delete Record PHP Methods	60	10/09/15
Query PHP Methods	120	10/09/15
Other code for logging in, browsing, logging out, sessions/cookies, chatting/messages	900	10/24/15
Troubleshoot	1800	10/26/15
Define server hardware and software requirements	60	10/26/15
Research laws	120	10/28/15
Create Acceptable Use Policy, Privacy Policy, Terms of Use	120	10/30/15

Total	3190	53.17	hours

## Actual Time Line
start	end	time	item
09/19/15	09/26/2015---	76	SDLC
09/19/15	10/30/15	35	Wamp
09/22/15	10/15/15	115	Database
09/23/15	10/25/15	90	Security
09/28/15	11/03/15	396	Design
09/28/15	11/03/15	631	PHP
10/03/15	10/05/15	105	Insert
10/03/15	10/22/15	277	Select
10/03/15	11/02/15	145	Update
10/05/15	10/26/15	48	Delete
10/08/15	10/30/15	40	Email
10/29/15	10/29/15	50	Policies
11/04/15	11/04/15	70	Soft/Hardware

## Specs
2 core 2.8 ghz
1gb ram
540mb for wamp installation
5mb for site pages
150kb per week per user
10gb database
~50gb+ depending on OS

100mb/s bandwidth
64bit WampServer 2.5
Apache 2.4.9
MySQL 5.6.17
PHP 5.5.12
PHPMyAdmin 4.1.14
SqlBuddy 1.3.3
XDebug 2.2.5

any modern browser

## Estimated vs Actual
Estimated		Actual
End	Time	End	Time	Item	Difference
09/25/15	150	10/15/15	115	Database	-35
10/09/15	240	10/26/15	48	Delete	-192
10/04/15	1140	11/03/15	396	Design	-744
10/08/15	240	10/05/15	105	Insert	-135
	180			Interview	-180
	120			Algorithm	-120
10/24/15	1340	11/03/15	651	PHP	-689
10/30/15	240	10/29/15	50	Policies	-190
09/19/15	90	09/26/15	76	SDLC	-14
09/23/15	240	10/25/15	90	Security	-150
10/09/15	300	10/22/15	277	Select	-23
10/26/15	60	11/04/15	70	Soft/Hardware	10
10/08/15	300	11/02/15	145	Update	-155
09/19/15	10	10/30/15	55	Wamp	45